## Sheet1
January Progress (01/01/2025 to 31/01/2025) | Changes & Issues | Status
Website Changes | 1. Added Form 2. Website Form size & Website language change issue 3. Profile changes 4. Updated sales mail content 5. Added clarity and amplitude script in website and all applications | Done
Cafe Issue Resolved | Wrong time issue | Done
BCP portal issue | .Net double slash issue | Done
Mawarid Welcome page update | 1. Gosi link updated 2. Added Insurance and Gosi as list like HR forms | Done
For Maintenance Application | 1. Removed Incomplete work order & work order task upto Aug 15, 2024 2. Added Maintenance technician filter in Helpdesk | Done
Flight Plan Line | 1. Added Flight plan Api and Generated CRM link 2. Flight Plan line - CRM form configuration issue | Done
Mawarid Test Environment | 1. Tested the Helpdesk in test envrionment and fixed the issues 2. Tested the Customer Support in test environment and fixed the issues | Done
Agent Portal issue | 1. Application Import Excel Sheet Issue | Done
Self Service Portal | 1. Added Description field in Item request lines in both create and list | Done
CRM | 1. Provided Helpdesk Ticket creation Api for CRM | Done
Sawaid Test Environment | 1. Tested the Helpdesk in test envrionment and fixed the issues 2. Tested the Customer Support in test environment and fixed the issues | Done
Sawaid Live Deployment | 1. Tested and found bugs in Helpdesk and Customer Support in SWD live 2. Bugs are fixed in Helpdesk and Customer Support live | Pending | Some bugs are pending 1. Export Data issue in Customer Support & Helpdesk 2. Helpdesk - My Team Requests - Pagination/Data issue & filter issue
Candidate Acceptance System | 1. Test Question Assignment issue 2. Changed the Test Name in Test Completion Certificate | Done
MWD Customer Support | 1. Invalid Recipient mail id issue while creating a ticket from system | Done
Document Management System | 1. User Create Issue | Done
Support Work for Mawarid directly and via helpdesk |  | Done