## Sheet1
March Progress (01/03/2025 to 31/03/2025) | Changes & Issues | Status
Website Changes | 1. Hemmah service request changes and added phone number validations 2. Updated url in hemma service 3. Hemma service request UI changes 4. Google ads issue for Hemah service request form 5. Added New Business request form in website 6. Updated New Business request form fields 7. Design issue in business request form in mobile view 8. New validations updated in the Business request form 9. Added Slider banner in Hemmah request form | Done
Helpdesk & Customer Support | 1. Deployed and Reviewed the Multiple attachment changes in helpdesk request create 2. Multiple attachment issue fixed in helpdesk 3. Added comments in status history and ticket comments in helpdesk and customer support 4. Configuration for Reopen mail by replying for closed tickets in Test Evt 5. Reviewed the Reopen mail by replying for closed tickets in Test Evt 6. Tested the Reply ticket reopen and coordinator mail notification functionality in mwd test & live 7. Helpdesk Maintenance task assignment issue 8. Add escalation mail and to show the scheduled date and assigned user name in the ticket list (InProgress) | Done
Jussur Support & Issues | 1. Jussur Bcp Crm api issue 2. Support in Jussur application crm link issue | Done
Agent Contract | 1. Discussed and Reviewed the Agent contract changes with Idhris bhai 2. Added New changes in Agent Contract by Idhris bhai 3. New changes in Agent Contract Appendix by Idhris bhai 4. Added New points of multiple approvers and signatures in Agent Contract | Done
Support Works | Customer support, Coordiator portal, Helpdesk, Self Service, Maintenance and Employee portal | Done
PPT & User Manual Documents | 1. Customer Support 2. Helpdesk 3. Coordinator Portal 4. Employee Portal 5. Agent Contract | Done