## Sheet1
December Progress (01/12/2024 to 31/12/2024) | Changes & Issues | Status
Website Changes | Added Email Subscription | Done
SDR changes by the Client (User Story 139: SDR - Test the Client Review changes) |  | Done
.Net Version Update | Updated to .Net 8 | Done
Version and Package deployment in apps4x |  | Done
Self service changes | 1. Changes in Loan Request Details 2. Change in Item Request Details 3. My Approvals details page 4. Hide Purchase Request | Done
Re-arranged the categories in helpdesk |  | Done
Email attachment issue fix (Customer Support) |  | Done
Sawaid Helpdesk deployment in Test Environment |  | Done
Multiple Attachment issue in Customer Support & Helpdesk | Issue fixed only in Customer Support | Pending
SDR Changes (Ref: 174 -Workitem) |  | Done
Change SDR Link in Welcome page & Update label as Live |  | Done
Helpdesk > Dashboard - Count mismatch in Request by Category chart |  | InProgress
Support work in Recruitment Project create and Removed the body from API |  | Done
New SDR changes for Relaese (Ref - User Story 267: SDR changes 30-12) |  | Done
New SDR Points (Ref - User Story 272: New SDR points - 31/12) |  | Done
Self Service > Item Request api issue on calling Bcp api (Ref - Bug 273: Item Request api issue) |  | Done
Mawarid Support works & Helpdesk tickets |  | Done